## Sheet1
Assembly steps | repeated duration (seconds) | one-time duration (minutes) | total minutes per device (for 40) | total hours per batch (for 40) | total price per batch
Nestbox PCB assembly and cabling | 890 | 1515 | 52.7083 | 35.1389 | 1159.5833
Set up drill for user button |  | 5 | 0.125 | 0.083333 | 2.75
Drill user button hole | 10 |  | 0.16667 | 0.11111 | 3.6667
Screw in user button | 30 |  | 0.5 | 0.33333 | 11
Solder user button to mainboard | 30 |  | 0.5 | 0.33333 | 11
Screw in both cable holders | 50 |  | 0.83333 | 0.55556 | 18.3333
Insertboth connector cables | 30 |  | 0.5 | 0.33333 | 11
Screw in connector cables | 60 |  | 1 | 0.66667 | 22
Solder connector cables (8 connections) | 80 |  | 1.3333 | 0.88889 | 29.3333
Define color code |  | 10 | 0.25 | 0.16667 | 5.5
insert SD card | 20 |  | 0.33333 | 0.22222 | 7.3333
Solder openLog | 80 |  | 1.3333 | 0.88889 | 29.3333
Insert waterproof joint | 30 |  | 0.5 | 0.33333 | 11
Soldering ESP12S | 60 |  | 1 | 0.66667 | 22
Soldering Battery connector to PCB | 20 |  | 0.33333 | 0.22222 | 7.3333
Attaching battery connector to battery holder | 50 |  | 0.83333 | 0.55556 | 18.3333
Sticking battery holder to case lid | 20 |  | 0.33333 | 0.22222 | 7.3333
printing and sticking label to lid | 20 |  | 0.33333 | 0.22222 | 7.3333
PCBA ordering and coordination with factory |  | 360 | 9 | 6 | 198
other parts ordering |  | 480 | 12 | 8 | 264
enclosure assembly and packaging | 300 |  | 5 | 3.3333 | 110
PCB Re-design for automatic Manufacturing |  | 480 | 12 | 8 | 264
Parts list update to match inventory of factory |  | 180 | 4.5 | 3 | 99
|  |  | 0 | 0 | 0
RFID reader PCB assembly and testing | 980 | 1055 | 42.7083 | 28.4722 | 939.5833
Setup Pick & Place machine |  | 240 | 6 | 4 | 132
Setup solder paste frame |  | 30 | 0.75 | 0.5 | 16.5
Apply solder paste | 120 |  | 2 | 1.3333 | 44
Place on PNP machine | 60 |  | 1 | 0.66667 | 22
Run PNP job | 120 |  | 2 | 1.3333 | 44
Place in reflow oven | 60 |  | 1 | 0.66667 | 22
manual correction | 60 |  | 1 | 0.66667 | 22
solder antenna | 20 |  | 0.33333 | 0.22222 | 7.3333
setup frequency test installation |  | 5 | 0.125 | 0.083333 | 2.75
test resonance frequency | 60 |  | 1 | 0.66667 | 22
adjust resonance capacitor and retest, if needed | 240 |  | 4 | 2.6667 | 88
PCB ordering and coordination with factory |  | 180 | 4.5 | 3 | 99
order & retrieve parts |  | 300 | 7.5 | 5 | 165
solder RFID cables to board | 240 |  | 4 | 2.6667 | 88
PCB Re-design for Mass-Manufacturing |  | 300 | 7.5 | 5 | 165
|  |  | 0 | 0 | 0
RFID mechanical assembly | 1420 | 525 | 36.7917 | 24.5278 | 809.4167
setup drill for antenna hole |  | 10 | 0.25 | 0.16667 | 5.5
cut perch | 60 |  | 1 | 0.66667 | 22
drill antenna hole | 10 |  | 0.16667 | 0.11111 | 3.6667
setup laser cutter |  | 20 | 0.5 | 0.33333 | 11
laser cut antenna pad 3 layers | 120 |  | 2 | 1.3333 | 44
laser cut load cell connecting MDF | 30 |  | 0.5 | 0.33333 | 11
unsolder antenna and insert through hole | 60 |  | 1 | 0.66667 | 22
resolder antenna and place into box | 60 |  | 1 | 0.66667 | 22
setup space and mix potting liquid |  | 15 | 0.375 | 0.25 | 8.25
pour potting liquid in box | 180 |  | 3 | 2 | 66
remove from potting environment | 60 |  | 1 | 0.66667 | 22
glue antenna pads together | 300 |  | 5 | 3.3333 | 110
screw antenna pad to perch | 120 |  | 2 | 1.3333 | 44
screw RFID box to MDF piece | 120 |  | 2 | 1.3333 | 44
screw mdf piece with load cell to perch | 300 |  | 5 | 3.3333 | 110
Mechanical Design for Mass-Manufacturing |  | 480 | 12 | 8 | 264
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
Load cell assembly | 720 | 270 | 18.75 | 12.5 | 412.5
define color code for connector |  | 20 | 0.5 | 0.33333 | 11
solder connector to cables | 240 |  | 4 | 2.6667 | 88
tighten connector with cables | 240 |  | 4 | 2.6667 | 88
setup drill for metallic parts alignment |  | 10 | 0.25 | 0.16667 | 5.5
drill metallic parts | 120 |  | 2 | 1.3333 | 44
screw load cell onto angle | 120 |  | 2 | 1.3333 | 44
parts ordering and retrieval |  | 240 | 6 | 4 | 132
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
Programming the boards | 520 | 60 | 10.1667 | 6.7778 | 223.6667
create efficient flashing setup for ESP |  | 20 | 0.5 | 0.33333 | 11
flashing the ESP | 60 |  | 1 | 0.66667 | 22
reconfigure the UART jumpers of the ESP | 60 |  | 1 | 0.66667 | 22
create efficient flashing setup for MSP |  | 20 | 0.5 | 0.33333 | 11
flashing RTC cal for MSP | 60 |  | 1 | 0.66667 | 22
measure RTC cal signal | 60 |  | 1 | 0.66667 | 22
calculate RTC cal correction registers |  | 20 | 0.5 | 0.33333 | 11
configure rtc cal registers in code | 100 |  | 1.6667 | 1.1111 | 36.6667
build and flash final firmware to MSP | 180 |  | 3 | 2 | 66
|  |  | 0 | 0 | 0
Labeling, packaging, delivery, reporting |  | 480 | 12 | 8 | 264
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
Safety margin | 3624 | 1562 | 99.45 | 66.3 | 2187.9
Move between steps (20% overhead) | 906 | 781 | 34.625 | 23.0833 | 761.75
Unexpected additional steps (20%) | 906 | 781 | 34.625 | 23.0833 | 761.75
Unexpected failures/design errors (40%) | 1812 |  | 30.2 | 20.1333 | 664.4
| repeated tasks | one-time tasks
Total | 8154 | 5467 | 272.575 | 181.7167 | 5996.65
Total hours for batch of 40 |  | 91.1167
Total hours per device (batch of 40) | 2.265 | 2.2779
Total cost per device (batch of 40) | 74.745 | 75.1713
Summary: |  |  | (Comparison with smaller batch size):
Number of Devices | 40 |  | Number of Devices |  | 10
Cost per hour | 33 |  | Cost per hour |  | 33
Total minutes per device | 272.575 |  | Total minutes per device |  | 634.6
Total hours per device | 4.5429 |  | Total hours per device |  | 10.5767
Total cost per device | 149.9163 |  | Total cost per device |  | 349.03
TOTAL TIME (hours) | 181.7167 |  | TOTAL TIME (hours) |  | 105.7667
TOTAL COST | 5996.65 |  | TOTAL COST |  | 3490.3